|  | Target | Action | Person responsible | When | Cost | RAG | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| F1 | Ensure ongoing core funding | Discussions with Town/ Warwick/ County Councils | Sim; Mandy | Sept-Dec annually |  |  |  |
| F2 | Ensure ongoing grant funding | Establish annual targets Investigate grant opportunities Monitor against target | Becky W; Sim |  |  |  | Finance sub cttee review three monthly |
| F3 | Develop and sustain sources of additional income | Establish list of potential funders and target figures. - Major sponsors; Approach potential funders (‘Friends of tKC’) at levels: - 200 people/ families @ £100; - Lower donations | (Victoria) Mandy Sarah+ Becky W; supporting volunteers TBA | Jan 2024 Jan-Mar work-shops From March on |  |  | Centre managers review monthly For trustees in 2024 |
| F4 | Increase lettings income by ( )% | Research competitor provision Research company & private needs Identify where investment could increase activities and/or income Develop further marketing activities | Sarah Sarah, Louise, Nigel | Feb 2024 2x1hr mtgs | tba tba |  | Main Hall & Youth Room targets of +40% Agreed targets led by Louise & Nigel |
| F5 | Monitor energy costs and seek opportunities for net cost reduction | Establish current costs and negotiate with energy companies for optimal fee structures Investigate options for solar panels | Sim Graham | Jan 2024 & annually 2024 2025 |  |  | Sim to lead and establish timescales |
| F6 | Ensure adequate three-year rolling funding stream. | Review F1, F2, F3 & F4 | Chair/trustees | July annually |  |  |  |
| F7 | Buildings lease and maintenance: develop and implement a sustainable model. | Discussions with stakeholders, especially Warks County Council covering: - buildings lease options - commissioning a buildings survey - opportunities to reduce volatility in maintenance costs | Sim; Mandy; Sarah | July 2024 |  |  | See LM5 |
| F8 | Investigate legal implications of maintenance volunteer | Ensure legal liability issues are secure | Sarah; Angela (HR) | Jan 2024 |  |  |  |
| F9 | Ensure tKC activities/ provision have optimal income streams | Identify costs of provision, including contribution to overheads. Ensure income covers costs, where possible. | Trustees; Sarah; Becky W |  |  |  | Links with Provision plan and F2 |
| F10 | Ensure lettings activities/ provision have optimal income streams | Identify costs of provision, including contribution to overheads. Ensure income covers costs, where possible. | Trustees; Sarah; Becky W |  |  |  | Links with F4 |
| F11 | Increase business development provision to match needs cost effectively | Analyse current provision of- - Business lettings - Abbey End Studios - Youth and Community to identify opportunities for growth. Identify where investment could increase activities and/or income. Review/ revise current publicity to increase effectiveness. Ensure that new provision is covered by net income streams | Becky J Sarah Becky W | From 2025 |  |  | Abbey End Studios a priority for 2024 Links with Provision plan |
| F12 | Develop marketing plan | - SWOT analysis of current marketing - Develop enhanced/ new marketing for activities/ provision - Establish what simple things can be outsourced, eg.press release templates - Raise knowledge and awareness of marketing among trustees | Centre managers with trustees | TBA TBA TBA |  |  | Trustees to monitor development of sustainable sponsorships and fundraising and market opportunities. A communications document is already done but needs tidying and a workshop for trustees to raise awareness is needed |
| F13 | Establish finance policies | Develop finance policies for centre staff (eg expenditure limits; tender processes) | Sim/ trustees | TBA |  |  | Urgently needed for staff and trustees to be confident of financial security |