|  | Target | Action | Funding source | Person responsible | When | Cost | RAG | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| P1 | New/ enhanced provision. Identify and establish priorities in responding to unmet need: consider provision under four themes- A Youth Provision Community Wellbeing B Radio Abbey Abbey End Studios | Check lists for completeness including with stakeholders. Prioritise in order to - meet greatest need - provide funded, high quality provision - optimise desired outcomes | Grants; Sponsorship; Donations | A Becky W; Becky J; Nick; Mandy B Sarah; (Victoria); Nigel | Monitor Jan and July annually Monitor monthly to July 2024, then review | TBA TBA |  | RAG level to be discussed at monitoring meetings RAG level to be discussed at monitoring meetings |
| P2 | Identify opportunities for net income generation. Research opportunities of running income-generating courses and their related potential net income streams. | Check lists for completeness including with stakeholders. Prioritise in order to - provide net positive income - provide high quality provision - optimise desired outcomes for stakeholders and tKC (eg word-of-mouth marketing) Specifically- Autism Support (WDC)/ Partners? Life skills classes- babysitting/ cooking/ CPE classes Nursery birthday party lettings Business Forum to identify what businesses want/ need. Continue support for local businesses with ‘lower cost spaces’ Improve spaces to increase appeal to more corporate audiences. |  | Trustees/ managers/ Centre staff Mandy Becky J | Review annually from 2025? From 2025? TBA |  |  | Low immediate priority. Trustee’s agenda item for ideas All to look for opportunities Lower priority. Review/ discuss in 2025 Maintain visibility. Sound booth- sharing ideas (new trustee needed) |
| P3 | Review current provision and Liaise with Compassionate Kenilworth/ Warwick District Council, stakeholders and others to identify optimal delivery mechanisms/ appropriate delivery locations/ equipment implications/ building adaptations. Establish current delivery costs to inform future provision and potential funding streams (including for different demographics) | SWOT analysis. User feedback for improvement of provision and marketing material. |  | Becky W. Trustee needed |  |  |  | Discuss at January 2024 trustee mtg? |