|  | Target | Action | Person responsible | Target Date | RAG | Progress to date |
| --- | --- | --- | --- | --- | --- | --- |
| F1 | Ensure ongoing core funding | Discussions with- - Town Council - Warwick District Council - Warwickshire County Council | Sim; Mandy | Feb and July |  | Meeting held – Minutes Available – Next Actions – Detailed maintenance report required |
| F2 | Ensure ongoing grant funding | - Establish annual targets - Investigate grant opportunities - Monitor income against targets | Becky W; Sim | Feb July |  |  |
| F3 | Develop and sustain sources of additional income | Establish list of potential funders and target figures for- - Major sponsors; Other potential funders (‘Friends of tKC’) at levels: - 200 people/ families @ £100; - Lower donations | Mandy Sarah+ Becky W; supporting volunteers TBA | Feb March on |  | 200 for 100 is live on the website – Sim looking into the 41 Club – SMc & Becky hosting Business forums and looking for further business support NB: I still there is a question over our clear story, Why do we need help? |
| F4 | Increase lettings income by ( )% Main Hall & Youth Room targets of +40% Agree targets for other areas | - Research competitor provision - Research company & private needs - Identify where investment could increase activities and/or income - Develop further marketing activities | Sarah Sarah, Louise, Nigel | Feb March |  | Sarah has produced a report available on the portal at last meeting Engage with business over use for events/ increase interest in Abbey End Studios – Main Press release going out 1st week of March |
| F5 | Monitor energy costs and seek opportunities for net cost reduction | Establish current costs and negotiate with energy companies for optimal fee structures Investigate options for solar panels | Sim Graham | Jan July |  |  |
| F6 | Ensure adequate three-year rolling funding stream. | Review F1, F2, F3 & F4 | Chair/trustees | July |  |  |
| F7 | Buildings lease and maintenance: develop and implement a sustainable model. | Discussions with stakeholders, especially Warks County Council covering: - buildings lease options - commissioning a buildings survey - opportunities to reduce volatility in maintenance costs | Sim; Mandy; Sarah | July |  | See LM5 |
| F8 | Investigate legal implications of maintenance volunteer | Ensure legal liability issues are secure | Sarah; Angela (HR) | Jan |  |  |
| F9 | Ensure tKC activities/ provision have optimal income streams | Identify costs of provision, including contribution to overheads. Ensure income covers costs, where possible. | Trustees; Sarah; Becky W |  |  | Links with Provision plan and F2 |
| F10 | Ensure lettings activities/ provision have optimal income streams | Identify costs of provision, including contribution to overheads. Ensure income covers costs, where possible. | Trustees; Sarah; Becky W |  |  | Links with F4 |
| F11 | Increase business development provision to match needs cost effectively | Analyse current provision of- - Business lettings - Abbey End Studios - Youth and Community to identify opportunities for growth. Identify where investment could increase activities and/or income. Review/ revise current publicity to increase effectiveness. Ensure that new provision is covered by net income streams | Becky J Sarah Becky W | From 2025 |  | Abbey End Studios a priority for 2024 Links with Provision plan |
| F12 | Develop marketing plan | - SWOT analysis of current marketing - Develop enhanced/ new marketing for activities/ provision - Establish what simple things can be outsourced, eg.press release templates - Raise knowledge and awareness of marketing among trustees | Centre managers with trustees | Sept (tba) |  | LM & SM have been working on social media planning and consistence. We could do with some PR help to look into the consistency of our messaging. |
| F13 | Establish finance policies | Develop finance policies for centre staff (including expenditure limits; tender processes etc) | Sim, Michael | Sept |  |  |